## Summary
Segment Information
Industry | Manufacturing | Sub Industry | Industrial Equipment Manufacturing
Country of Inc | India | Year Incoporated | < fill >
Client Information
Client Name | Tekman India Pvt Ltd
Entity Type | Pvt Ltd | Markets | < fill > | Tip: India, UAE, etc
Address | < fill > | Business Model | B2B | Tip: B2B / B2C / OEM / Export-driven
Website | < fill > | Industries Served | Manufacturing
Current Annual Turnover | < fill > | Top Customers | < fill >
Offices / Plants | Thane, Baroda
About the Client | <200-300 words from their website> | About Client's Products | <400-500 words from their website>
Key Business Priotities | Growth from New Markets | Growth from New Products | IPO after 100 Cr Rev | < fill >
| Reduce Manpower Dependency | Drive AI-led Transformation for Future | Succession Roadmap | < fill >
Leadership
Key Leader #1 | Sunil Joshi | MD & CEO | <email> ¦ <phone> ¦ Loc | Key Decision Maker
Key Leader #2 | Prasad Jagtap | Dir & Head of Sales | <email> ¦ <phone> ¦ Loc | Key Decision Influencer
Key Leader #3 | Karishma Shetty | CFO, Legal | <email> ¦ <phone> ¦ Loc | Key Decision Influencer
Key Leader #4 | Neha Phadke | CHRO, CMO, Admin | <email> ¦ <phone> ¦ Loc
Key Leader #5 | Sujata Pawar | AI Champion #1 | <email> ¦ <phone> ¦ Loc | Nominated as AI Champion for S3K
Key Leader #6 | Sarita ?? | AI Champion #2 | <email> ¦ <phone> ¦ Loc | Nominated as AI Champion for S3K
Key Leader #7 | Vaishali ?? | CIO/IT | <email> ¦ <phone> ¦ Loc
Tech Ecosystem
CRM | Salesforce | Approx 10 Seats | IT Partner#1 | < fill >
ERP | < fill > |  | IT Partner#2 | < fill >
Cloud/Servers | < fill > |  | IT Partner#3 | < fill >
Finance | Tally |  | IT Partner#4 | < fill >
HRMS | < fill > |  | IT Partner#5 | < fill >
Office | Microsoft 365
Data/ML/AI | PowerBI
CoPilot
< fill >

## Sales
S#1 | Scope / Opportunity | Duration | Value | Status | Key Milestones | Comments
0 | Lead Gen & Sales Cycle Started |  | 0 |  | 2025-06-16 | Hrishi, Rujuta met Sunil and Co through Prasad's connects
1 | AI Exec Briefing & Discovery Workshop | 1 Day | 100000 | Completed | 2026-02-23 | In Person, Thane Client Office
2 | AI COE | 12 Months | 1200000 | In Progress | 2026-03-16 | 1 FTE

## AI Usecases Tracker
Sr# | USE CASES | New Features Ideated | Complexity | Solution Category | Department | Ideation | Design & Dev | UAT | Go-Live | Weekly Comments | <Make 7-8 Phases? / AI used / Tools
0 | Tekman Infra
1 | Chatbot SOP documents. | Add feature of Data Chat | Med | GenAI Conversational Knowledge Base Q&A | Entire Org | Done | Done | April | April
2 | GST Recon | Analytics, Email Action, Search, Name Chat with Data | Complex | SQL Based App, with GenAI features | Finance | Done | Done |  | May
3 | Sales PowerBI Dashboard |  | Med | Data Visualization | Sales | In Progress | April | April | April
4 | Co-pilot Email Automation |  | Low | MS Power Automate | Execs | High Level
5 | Sales Quotation, trading |  | TBD | AI App | Inside Sales | To be Planned
6 | Project Planning Advisor |  | V Complex | AI App | Core MFG | High Level
7 | Financial Cost Analysis |  | Complex | Data Visualization | Finance | High Level
8 | Market Research |  | TBD | AI App | Sales | To be Planned
9 | Product R&D Development |  | TBD | Deep Research Prompt | R&D | To be Planned
| Link to EPICS/USER STORIES App |  | JIRA or TBD

## AI Training Tracker
S#1 | Scope / Opportunity | Duration | Value | Status | Key Milestones | Comments
1 | AI Exec Briefing & Discovery Workshop | 1 Day | 100000 | Completed | 2026-02-23 | In Person, Thane Client Office
2 | CoPilot | 1 Day | 100000 | TBD | May | Part of the 1Lac/PM deal

## Weekly Email Report
S#1 | Date | Email Body | Attach Table | Status | Who
1 | 2026-03-27 | Subject: Weekly AI COE Progress Report ¦ Tekman (Week of 27-March-2026) Dear [Client Name / Team], Please find below the weekly update on AI use case development and training progress for the week. Key highlights: [1-line achievement: e.g., 2 AI use cases moved to prototype stage] [1-line training update: e.g., Completed GenAI fundamentals for 25 users] [1-line impact: e.g., Identified ~15–20% efficiency opportunity] Kindly review the updates and share your inputs, especially on the decisions required section. Regards, | From AI Usecases Tracker Tab, Training Tab | Sent of Time | Sameer Sawardekar
2 | 2026-04-03
3 | 2026-04-10
4 | 2026-04-17
5 | 2026-04-24
6 | 2026-05-01
7 | 2026-05-08
8 | 2026-05-15
9 | 2026-05-22
10 | 2026-05-29
Formulas:
Date = [Date, row above]+7

## Monthly Exec Review
S#1 | Date | Agenda | Attendees | Location | Status | Key Minutes | Key CTAs
1 | 2026-03-16
2 | 2026-04-15
3 | 2026-05-15
4 | 2026-06-14
5 | 2026-07-14
6 | 2026-08-13
7 | 2026-09-12
8 | 2026-10-12
9 | 2026-11-11
10 | 2026-12-11
11 | 2027-01-10
12 | 2027-02-09
Formulas:
Date = [Date, row above]+30

## Cost Tracker
S#1 | Dates | Days | Scope Delivered | Revenue Accrued | Cost ¦ Travel, Etc | Cost ¦ Licenses, if any | Cost ¦ Ext Freelancer, if any | Cost ¦ Full Time Resources | Cost ¦ Part Time Resources |  | Cost ¦ Part Time Resources |  | Total Cost | GM | GM%
[10 empty] | India Based |  | US Based
[10 empty] | Take 1100 Rs/Hr Cost |  | Take 2200 Rs/Hr Cost
0 | Jul25 to Feb 26 | 6 months | Sales Meetings | 0 |  |  |  |  | Hours/Month |  | Hours/Month
1 | 2026-02-26 | 1 | AI Exec Briefing & Discovery Workshop | 100000 | <Check from Neesha, for Claims> | <Check from Neesha, for Claims> | <Check from Neesha, for Claims> | <eg: Salary of Deepak 100%, 50% Armaan> |  | <TBD> |  | 1052.1886
2 | 2026-03-01 | 15 |  | 100000 | 1000 | 0 | 0 | 15000 | 0 | 0 | 10 | 22000 | 38000 | 62000 | 62%
3 | 2026-04-01 | 30 |  |  | <Check from Neesha, for Claims> | <Check from Neesha, for Claims> | <Check from Neesha, for Claims>
4 | 2026-05-01 | 30 |  |  | <Check from Neesha, for Claims> | <Check from Neesha, for Claims> | <Check from Neesha, for Claims>
5 | 2026-06-01 | 30 |  |  | <Check from Neesha, for Claims> | <Check from Neesha, for Claims> | <Check from Neesha, for Claims>
6 | 2026-07-01 | 30 |  |  | <Check from Neesha, for Claims> | <Check from Neesha, for Claims> | <Check from Neesha, for Claims>
7 | 2026-08-01 | 30 |  |  | <Check from Neesha, for Claims> | <Check from Neesha, for Claims> | <Check from Neesha, for Claims>
8 | 2026-09-01 | 30 |  |  | <Check from Neesha, for Claims> | <Check from Neesha, for Claims> | <Check from Neesha, for Claims>
9 | 2026-10-01 | 30 |  |  | <Check from Neesha, for Claims> | <Check from Neesha, for Claims> | <Check from Neesha, for Claims>
10 | 2026-11-01 | 30 |  |  | <Check from Neesha, for Claims> | <Check from Neesha, for Claims> | <Check from Neesha, for Claims>
12 | 2026-12-01 | 30 |  |  | <Check from Neesha, for Claims> | <Check from Neesha, for Claims> | <Check from Neesha, for Claims>
13 | 2027-01-01 | 30 |  |  | <Check from Neesha, for Claims> | <Check from Neesha, for Claims> | <Check from Neesha, for Claims>
14 | 2027-02-01 | 30 |  |  | <Check from Neesha, for Claims> | <Check from Neesha, for Claims> | <Check from Neesha, for Claims>